## Task_Table
ID | Active | Task Mode | Name | Duration | Start | Finish | Predecessors | Outline Level | Notes
1 | Yes | Manually Scheduled | Order # _Customer _Project Name | 117.12 days | Wed 3/16/22 | Thu 8/25/22 |  | 1 | Yellow highlighted cells will be filled by technical Lead and reviewed by PM and SDM
2 | Yes | Auto Scheduled | Contingency | 20 days? | Wed 3/16/22 | Sun 4/17/22 |  | 2
3 | Yes | Auto Scheduled | Project Management Activities | 80 days? | Wed 3/16/22 | Thu 7/21/22 |  | 2 | PM Activities Include the following Tasks · Review Project Documentation · Conduct KOM (Internal with the Team & External with the customer) · Sales Handover Meeting · Prepare/Update Risk Plan & high level project schedule · Update detailed project Schedule · Customer Status Report · Tasks Progress Status with TL and team
4 | Yes | Auto Scheduled | Technical Activities / Detailed WBS | 78 days | Mon 3/28/22 | Wed 7/13/22 |  | 2
5 | Yes | Auto Scheduled | Technical Processes Activities | 78 days | Mon 3/28/22 | Wed 7/13/22 |  | 3
6 | Yes | Auto Scheduled | Analysis | 13 days | Mon 3/28/22 | Wed 4/13/22 |  | 4
7 | Yes | Auto Scheduled | Data Gathering | 6 days | Mon 3/28/22 | Mon 4/04/22 |  | 5
8 | Yes | Auto Scheduled | Data Gathering - ECM Analyst | 3.5 days? | Mon 3/28/22 | Sun 4/03/22 |  | 6
9 | Yes | Manually Scheduled | Data Gathering - ECM Tech Lead | 1 day | Mon 4/04/22 | Mon 4/04/22 | 8 | 6
10 | Yes | Auto Scheduled | Analysis Document Preparation | 2.75 days | Sun 4/03/22 | Tue 4/05/22 |  | 5
11 | Yes | Auto Scheduled | Analysis Document Preparation - ECM Analyst | 2.75 days? | Sun 4/03/22 | Tue 4/05/22 |  | 6
12 | Yes | Auto Scheduled | Analysis Document Customer Review | 2 days | Wed 4/06/22 | Thu 4/07/22 |  | 5
13 | Yes | Auto Scheduled | Analysis Document Customer Review - ECM Analyst | 2 days? | Wed 4/06/22 | Thu 4/07/22 | 11 | 6
14 | Yes | Auto Scheduled | Analysis Document Rework | 1 day | Wed 4/13/22 | Wed 4/13/22 | 12 | 5
15 | Yes | Auto Scheduled | Analysis Document Rework - ECM Analyst | 1 day | Wed 4/13/22 | Wed 4/13/22 |  | 6
16 | Yes | Auto Scheduled | Design | 5.25 days | Thu 4/14/22 | Thu 4/21/22 | 6 | 4
17 | Yes | Auto Scheduled | Design Document Preparation | 3.75 days | Thu 4/14/22 | Tue 4/19/22 |  | 5
18 | Yes | Auto Scheduled | Design Document Preparation - ECM Tech | 3 days? | Thu 4/14/22 | Tue 4/19/22 |  | 6
19 | Yes | Auto Scheduled | Design Document Review with Tech Lead and Rework | 1.25 days | Wed 4/20/22 | Thu 4/21/22 | 17;82 | 5
20 | Yes | Auto Scheduled | Design Document Review with Tech Lead and Rework - ECM Tech | 1 day? | Wed 4/20/22 | Thu 4/21/22 |  | 6
21 | Yes | Auto Scheduled | Implementation | 30.75 days | Thu 4/21/22 | Thu 6/02/22 | 16 | 4
22 | Yes | Auto Scheduled | ECM Implementation | 30.25 days | Thu 4/21/22 | Thu 6/02/22 |  | 5
23 | Yes | Auto Scheduled | ECM Implementation - ECM Tech | 25 days? | Thu 4/21/22 | Thu 6/02/22 |  | 6
24 | Yes | Auto Scheduled | ECM Implementation Review with Tech Lead and Rework | 6 days | Thu 5/26/22 | Thu 6/02/22 |  | 5
25 | Yes | Auto Scheduled | ECM Implementation Review with Tech Lead and Rework - ECM Tech | 6 days? | Thu 5/26/22 | Thu 6/02/22 |  | 6
26 | Yes | Auto Scheduled | ECM Integration WS Implementation | 33.25 days | Tue 4/05/22 | Sun 5/22/22 |  | 4
27 | Yes | Auto Scheduled | Build Integration WS | 21.25 days | Tue 4/05/22 | Wed 5/04/22 |  | 5
28 | Yes | Auto Scheduled | Upload Document Function | 2 days? | Tue 4/05/22 | Thu 4/07/22 |  | 6
29 | Yes | Auto Scheduled | Retrieve Document Function | 2 days? | Thu 4/07/22 | Tue 4/12/22 | 28 | 6
30 | Yes | Auto Scheduled | Update document Service | 2 days? | Tue 4/12/22 | Thu 4/14/22 | 29 | 6
31 | Yes | Auto Scheduled | Delete Document Service | 2 days? | Sun 4/17/22 | Tue 4/19/22 | 30 | 6
32 | Yes | Auto Scheduled | Search for Document Service | 2 days? | Tue 4/19/22 | Sun 4/24/22 | 31 | 6
33 | Yes | Auto Scheduled | Documentation | 3 days? | Sun 4/24/22 | Wed 5/04/22 | 32 | 6
34 | Yes | Auto Scheduled | Testing | 2 days | Wed 5/04/22 | Sun 5/08/22 | 27 | 5
35 | Yes | Auto Scheduled | Testing the integation WS | 2 days? | Wed 5/04/22 | Sun 5/08/22 |  | 6
36 | Yes | Auto Scheduled | Deployment, UAT & GoLive | 10 days | Sun 5/08/22 | Sun 5/22/22 | 34 | 5
37 | Yes | Auto Scheduled | Deployment on Test | 2 days? | Sun 5/08/22 | Tue 5/10/22 |  | 6
38 | Yes | Auto Scheduled | Fix and Redeploy | 2 days? | Tue 5/10/22 | Thu 5/12/22 | 37 | 6
39 | Yes | Auto Scheduled | UAT | 4 days? | Thu 5/12/22 | Wed 5/18/22 | 38 | 6
40 | Yes | Auto Scheduled | Production Deployment | 2 days? | Wed 5/18/22 | Sun 5/22/22 | 39 | 6
41 | Yes | Auto Scheduled | Testing | 48 days | Wed 4/13/22 | Sun 6/19/22 |  | 4
42 | Yes | Auto Scheduled | Solution Deployment to TEST environment | 1 day | Sun 6/05/22 | Sun 6/05/22 |  | 5
43 | Yes | Auto Scheduled | Solution Deployment to TEST environment - ECM Tech | 1 day? | Sun 6/05/22 | Sun 6/05/22 | 23 | 6
44 | Yes | Auto Scheduled | Test Cases Design | 7.75 days | Wed 4/13/22 | Sun 4/24/22 |  | 5
45 | Yes | Auto Scheduled | Test Cases Design - ECM QC | 6 days? | Wed 4/13/22 | Sun 4/24/22 |  | 6
46 | Yes | Auto Scheduled | Test Cases Execution | 8 days | Mon 6/06/22 | Wed 6/15/22 |  | 5
47 | Yes | Auto Scheduled | Test Cases Execution - ECM QC | 8 days? | Mon 6/06/22 | Wed 6/15/22 | 43 | 6
48 | Yes | Auto Scheduled | Bug Fixing | 4 days | Thu 6/09/22 | Tue 6/14/22 |  | 5
49 | Yes | Auto Scheduled | Bug Fixing - ECM Tech | 4 days? | Thu 6/09/22 | Tue 6/14/22 |  | 6
50 | Yes | Auto Scheduled | Regression Retest | 2 days | Thu 6/16/22 | Sun 6/19/22 |  | 5
51 | Yes | Auto Scheduled | Regression Retest - ECM QC | 2 days? | Thu 6/16/22 | Sun 6/19/22 | 47 | 6
52 | Yes | Auto Scheduled | UAT | 11 days | Mon 6/20/22 | Mon 7/04/22 | 41 | 4
53 | Yes | Auto Scheduled | Solution Deployment to UAT environment | 1 day | Mon 6/20/22 | Mon 6/20/22 |  | 5
54 | Yes | Auto Scheduled | Solution Deployment to UAT environment - ECM Tech | 1 day? | Mon 6/20/22 | Mon 6/20/22 |  | 6
55 | Yes | Auto Scheduled | Solution Deployment Verification on UAT environment | 1 day | Tue 6/21/22 | Tue 6/21/22 | 53 | 5
56 | Yes | Auto Scheduled | Solution Deployment Verification on UAT environment - ECM Tech | 1 day? | Tue 6/21/22 | Tue 6/21/22 |  | 6
57 | Yes | Auto Scheduled | Solution Deployment Verification on UAT environment - ECM Analyst | 1 day? | Tue 6/21/22 | Tue 6/21/22 |  | 6
58 | Yes | Auto Scheduled | Conduct UAT Session(s) | 5 days | Wed 6/22/22 | Tue 6/28/22 | 55 | 5
59 | Yes | Auto Scheduled | Conduct UAT Session(s) - ECM Tech | 5 days? | Wed 6/22/22 | Tue 6/28/22 |  | 6
60 | Yes | Auto Scheduled | Implement UAT Session(s) Comments/Rework | 4 days | Wed 6/29/22 | Mon 7/04/22 | 58 | 5
61 | Yes | Auto Scheduled | Implement UAT Session(s) Comments/Rework - ECM Tech | 3 days? | Wed 6/29/22 | Mon 7/04/22 |  | 6
62 | Yes | Auto Scheduled | Training | 3 days | Tue 7/05/22 | Thu 7/07/22 | 52 | 4 | · The Payment Number should match the number that has been assigned to cash flow Item Type that equal Service in the Quotation · You should Fill the highlighted Cells to Calculate The (Bill In Days) The Bill in Days field is calculated as follow (Finish date for payment terms task ) - ( Estimate PO date ) · The Bill In Days should be greater than zero
63 | Yes | Auto Scheduled | Department User Guide Preparation | 2 days | Tue 7/05/22 | Wed 7/06/22 |  | 5 | · The Payment Number should match the number that has been assigned to cash flow Item Type that equal Service in the Quotation · You should Fill the highlighted Cells to Calculate The (Bill In Days) The Bill in Days field is calculated as follow (Finish date for payment terms task ) - ( Estimate PO date ) · The Bill In Days should be greater than zero
64 | Yes | Auto Scheduled | Department User Guide Preparation - ECM Analyst | 2 days? | Tue 7/05/22 | Wed 7/06/22 |  | 6 | · The Payment Number should match the number that has been assigned to cash flow Item Type that equal Service in the Quotation · You should Fill the highlighted Cells to Calculate The (Bill In Days) The Bill in Days field is calculated as follow (Finish date for payment terms task ) - ( Estimate PO date ) · The Bill In Days should be greater than zero
65 | Yes | Auto Scheduled | Department End User Training (Train the Trainer) | 1 day | Thu 7/07/22 | Thu 7/07/22 |  | 5 | · The Payment Number should match the number that has been assigned to cash flow Item Type that equal Service in the Quotation · You should Fill the highlighted Cells to Calculate The (Bill In Days) The Bill in Days field is calculated as follow (Finish date for payment terms task ) - ( Estimate PO date ) · The Bill In Days should be greater than zero
66 | Yes | Auto Scheduled | Department End User Training (Train the Trainer) - ECM Analyst | 1 day? | Thu 7/07/22 | Thu 7/07/22 | 64 | 6
67 | Yes | Auto Scheduled | Department Admin Guide Preparation | 1 day | Tue 7/05/22 | Tue 7/05/22 |  | 5
68 | Yes | Auto Scheduled | Department Admin Guide Preparation - ECM Tech | 1 day? | Tue 7/05/22 | Tue 7/05/22 |  | 6
69 | Yes | Auto Scheduled | Department Admin User Training (Train the Trainer) | 1 day | Wed 7/06/22 | Wed 7/06/22 |  | 5
70 | Yes | Auto Scheduled | Department Admin User Training (Train the Trainer) - ECM Tech | 1 day? | Wed 7/06/22 | Wed 7/06/22 | 68 | 6
71 | Yes | Auto Scheduled | Go Live | 7 days | Tue 7/05/22 | Wed 7/13/22 | 41 | 4
72 | Yes | Auto Scheduled | Solution Deployment to PROD environment | 3 days | Tue 7/05/22 | Thu 7/07/22 |  | 5
73 | Yes | Auto Scheduled | Solution Deployment to PROD environment - ECM Tech | 3 days? | Tue 7/05/22 | Thu 7/07/22 | 61 | 6
74 | Yes | Auto Scheduled | Solution Deployment Verification on PROD environment | 2 days | Tue 7/12/22 | Wed 7/13/22 |  | 5
75 | Yes | Auto Scheduled | Solution Deployment Verification on PROD environment - ECM Tech | 2 days? | Tue 7/12/22 | Wed 7/13/22 | 73 | 6
76 | Yes | Auto Scheduled | Cost Of Warranty Period 2.5 Y -20% utilization | 127 days | Sun 10/02/22 | Mon 3/27/23 |  | 1 | This field will be filled in case the project includes Warranty Period after The delivery
77 | Yes | Auto Scheduled | Buffer | 33.25 days | Tue 4/05/22 | Sun 5/22/22 |  | 1

## Resource_Table
ID | Indicators | Resource name | Type | Material label | Initials | Group | Max.Units | Std.Rate | Ovt.Rate | Cost/Use | Accrue At | Base Calendar | Code
1 |  | IM (Blended) | Work |  | I | Generic | 100% | ج.م.‏318.00/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
2 |  | Industry PMs (Blended) | Work |  | I | Generic | 100% | ج.م.‏403.00/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
3 |  | Maha Maurice | Work |  |  | Industry Solutions | 100% | ج.م.‏477.00/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
4 |  | Mohamed Essam | Work |  |  | Industry Solutions | 100% | ج.م.‏249.69/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
5 |  | Mohamed Hisham | Work |  |  | Quality Control | 100% | ج.م.‏177.02/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
6 |  | Wael Ramzy | Work |  |  | Industry Solutions | 100% | ج.م.‏182.25/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
7 |  | Yehia Mohamed | Work |  |  | Industry Solutions | 100% | ج.م.‏194.00/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
8 |  | Sherif Gamal | Work |  |  | Quality Control | 100% | ج.م.‏133.85/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
9 |  | Mohamed ElShahat | Work |  |  | Industry Solutions | 100% | ج.م.‏339.96/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
10 |  | Business Analysis (Blended) | Work |  | B | Generic | 100% | ج.م.‏323.05/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises
11 |  | QC & CM (Blended) | Work |  | Q | Generic | 100% | ج.م.‏251.00/hr | ج.م.‏0.00/hr | ج.م.‏0.00 | Prorated | Intercom Enterprises

## Assignment_Table
ID | Task name | Resource name | Work | Duration
389 | Contingency | IM (Blended) | 20 days | 20 days?
791 | Department User Guide Preparation - ECM Analyst | Wael Ramzy | 2 days | 2 days?
1698 | Analysis Document Rework - ECM Analyst | Wael Ramzy | 1 day | 1 day
1725 | Solution Deployment Verification on UAT environment - ECM Analyst | Wael Ramzy | 1 day | 1 day?
1731 | Department End User Training (Train the Trainer) - ECM Analyst | Wael Ramzy | 1 day | 1 day?
1758 | Project Management Activities | Maha Maurice | 20 days | 80 days?
1759 | Cost Of Warranty Period 2.5 Y -20% utilization | IM (Blended) | 125 days | 127 days
1762 | Data Gathering - ECM Analyst | Wael Ramzy | 1.39 days | 3.5 days?
1763 | Data Gathering - ECM Analyst | Yehia Mohamed | 1.39 days | 3.5 days?
1764 | Data Gathering - ECM Tech Lead | Mohamed Essam | 0.5 days | 1 day
1765 | Data Gathering - ECM Tech Lead | Wael Ramzy | 0.5 days | 1 day
1767 | Analysis Document Preparation - ECM Analyst | Yehia Mohamed | 2 days | 2.75 days?
1768 | Analysis Document Preparation - ECM Analyst | Wael Ramzy | 2 days | 2.75 days?
1776 | Analysis Document Customer Review - ECM Analyst | Wael Ramzy | 2 days | 2 days?
1782 | Test Cases Design - ECM QC | Sherif Gamal | 6 days | 6 days?
1783 | Test Cases Execution - ECM QC | Sherif Gamal | 8 days | 8 days?
1784 | Regression Retest - ECM QC | Sherif Gamal | 2 days | 2 days?
1785 | Data Gathering - ECM Analyst | Mohamed ElShahat | 1.22 days | 3.5 days?
1787 | Design Document Preparation - ECM Tech | Wael Ramzy | 3 days | 3 days?
1790 | Design Document Review with Tech Lead and Rework - ECM Tech | Mohamed Essam | 1 day | 1 day?
1791 | Design Document Review with Tech Lead and Rework - ECM Tech | Wael Ramzy | 1 day | 1 day?
1792 | ECM Implementation - ECM Tech | Yehia Mohamed | 25 days | 25 days?
1795 | ECM Implementation Review with Tech Lead and Rework - ECM Tech | Mohamed Essam | 3 days | 6 days?
1796 | ECM Implementation Review with Tech Lead and Rework - ECM Tech | Yehia Mohamed | 3 days | 6 days?
1811 | Upload Document Function | Mohamed ElShahat | 2 days | 2 days?
1812 | Retrieve Document Function | Mohamed ElShahat | 2 days | 2 days?
1813 | Update document Service | Mohamed ElShahat | 2 days | 2 days?
1814 | Delete Document Service | Mohamed ElShahat | 2 days | 2 days?
1815 | Search for Document Service | Mohamed ElShahat | 2 days | 2 days?
1816 | Documentation | Mohamed ElShahat | 3 days | 3 days?
1818 | Testing the integation WS | Mohamed ElShahat | 2 days | 2 days?
1819 | Production Deployment | Mohamed ElShahat | 2 days | 2 days?
1820 | UAT | Mohamed ElShahat | 4 days | 4 days?
1821 | Deployment on Test | Mohamed ElShahat | 2 days | 2 days?
1822 | Fix and Redeploy | Mohamed ElShahat | 2 days | 2 days?
1824 | Solution Deployment to TEST environment - ECM Tech | Yehia Mohamed | 1 day | 1 day?
1825 | Bug Fixing - ECM Tech | Yehia Mohamed | 4 days | 4 days?
1826 | Solution Deployment to UAT environment - ECM Tech | Yehia Mohamed | 1 day | 1 day?
1827 | Solution Deployment Verification on UAT environment - ECM Tech | Yehia Mohamed | 1 day | 1 day?
1828 | Conduct UAT Session(s) - ECM Tech | Wael Ramzy | 5 days | 5 days?
1829 | Implement UAT Session(s) Comments/Rework - ECM Tech | Yehia Mohamed | 3 days | 3 days?
1830 | Department Admin Guide Preparation - ECM Tech | Yehia Mohamed | 1 day | 1 day?
1831 | Department Admin User Training (Train the Trainer) - ECM Tech | Yehia Mohamed | 1 day | 1 day?
1832 | Solution Deployment to PROD environment - ECM Tech | Yehia Mohamed | 3 days | 3 days?
1833 | Solution Deployment Verification on PROD environment - ECM Tech | Yehia Mohamed | 2 days | 2 days?
1836 | Analysis Document Internal Reviews - ECM Tech | IM (Blended) | 2 days | 2 days?
1838 | Design Document Preparation - ECM Tech | IM (Blended) | 2 days | 2 days?
1847 | Analysis Document Internal Reviews - ECM Analyst | Business Analysis (Blended) | 2 days | 2 days?
1848 | Analysis Document Internal Reviews - ECM QC | QC & CM (Blended) | 2 days | 2 days?
1849 | Upload Document Function | IM (Blended) | 3 days | 3 days?
1856 | Retrieve Document Function | IM (Blended) | 3 days | 3 days?
1857 | Update document Service | IM (Blended) | 3 days | 3 days?
1858 | Delete Document Service | IM (Blended) | 3 days | 3 days?
1859 | Search for Document Service | IM (Blended) | 3 days | 3 days?
1860 | Documentation | IM (Blended) | 2 days | 2 days?
1861 | Testing the integation WS | IM (Blended) | 8 days | 8 days?